## Product Backlog
PRODUCT BACKLOG FOR WEB ENABLED ROLE BASED SYSTEM (GROUP CW)
ID | As a… | I want to be able to… | So that… | Priority | Sprint | Status
1 | Staff | Login into the system | I am able to submit ideas | MUST | 1 | Done | Done
2 | Staff | Sign up to the system | I can have an account in order to access the system | MUST | 1 | Done
3 | Staff | read the terms & conditions | I knowwhat T&C is | MUST | 1 | Done | Next Progress
4 | Staff | agree to the terms & conditions | I am able to submit ideas | MUST | 1 | Done
5 | Staff | choose to upload a pdf document | I am able to support my ideas | MUST | 1 | Done | To be Started
6 | Staff | add tags to my ideas | I am able to categorize them | SHOULD | 2 | Done
7 | Staff | see the ideas of other people | I can keep that as a reference for my submission | COULD | 2 | Done
8 | Staff | see the ideas of other people | I can comment on their ideas | SHOULD | 3 | Done
9 | Staff | be invisible through my ideas | I can be free in terms of sharing contents | WON'T | 3 | Done
10 | Staff | receive confirmation email / notification | I know I have successfully submitted the ideas | MUST | 3 | Done
11 | Staff | see the ideas of other people | I can react to them | SHOULD | 3 | Done
12 | Staff | choose to be visible | My ideas can be seen by other people | MUST | 4 | Done
13 | QA Coordinator | acces the system | I am able to track all the latest ideas of staffs | MUST | 4 | Done
14 | QA Manager | access the system | I am to oversee all the process | MUST | 4 | Done
15 | QA Manager | add new category | Categories will be seen in the main forum page | MUST | 4 | Done
16 | QA Manager | delete any latest or old ideas | Categories will be reduced once its not being used | SHOULD | 4 | Done
17 | Staff | upload any relevant files to my idea | Uploaded files can be seen in the posted idea | SHOULD | 4 | Done
18 | QA Coordinator | upload any relevant files to my idea | Uploaded files can be seen in the posted idea | MUST | 4 | Done
19 | QA Coordinator | see the statistics of the entire portal | I can keep track on the overall performance of the forum | MUST | 4 | Done
20 | QA Manager | ban any staffs or coordinators from posting ideas | There won't be any inappropriate contents in the forum | MUST | 4 | Done
21 | QA Manager | upload any relevant files to my idea | Uploaded files can be seen in the posted idea | MUST | 4 | Done
22 | QA Manager | upload any supporting document | I am able to see the files in the idea section | MUST | 4 | Done
23 | Admin | maintain all the system's data | system will be up to date | MUST | 4 | Done

## Sprint 1
Task | Time (estimated) [DAYS] | Time (spent) | Time (left) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | Done By | Tested By
As a staff, I want to login into the system so that I am able to submit ideas. | 1 | 1 | 0 | 1 | [13 empty] | Kai Lin | Brian Ee
As a staff, I want to sign up to the system so that I can have an account in order to access the system. | 5 | 5 | 0 |  | 1 | 1 | 1 | 1 | 1 | [8 empty] | Kai Lin | Kajen
As a staff, I want to read the terms and conditions so that I am able to submit ideas into the system. | 4 | 4 | 0 |  |  |  | 1 | 1 | 1 | 1 | [7 empty] | Brian Ee | Keerthigai
As a staff, I want to agree to the terms and conditions so that I am able to submit ideas into the system. | 8 | 8 | 0 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Brian Ee | Min qi
Implement "Delete Course" Business Logic (Code) | 0 | 0 | 0
Test for "Delete Course" function | 0 | 0 | 0
Research how to create PDF file | 0 | 0 | 0
Implement create PDF file function (to download) | 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
TOTAL | 18 | 18 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2
Daily burnout | 2.6 |  |  | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1
Total time left (from estimate) |  | Estimate | 18 | 16.9 | 15.8 | 14.7 | 13.6 | 12.5 | 11.4 | 10.3 | 9.2 | 8.1 | 7 | 5.9 | 4.8 | 3.7 | 2.6
Total time left (from spent) |  | Burnout | 18 | 17 | 16 | 15 | 13 | 11 | 9 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0

## Sprint 2
Task | Time (estimated) [DAYS] | Time (spent) | Time (left) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | Done By | Tested By
As a staff I want to choose to upload a pdf document so that I am able to support my ideas. | 3 | 3 | 0 | 1 | 1 | 1 | [11 empty] | Kai Lin | Kajen
As a staff I want to add tags to my ideas so that I am able to categorize them. | 3 | 3 | 0 |  | 1 | 1 | 1 | [10 empty] | Kai Lin | Min qi
As a staff I want to see the ideas of other people so that I can keep that as a reference for my submission. | 2 | 2 | 0 |  |  | 1 | 1 | [10 empty] | Kai Lin | Brian
As a staff I want to see the ideas of other people so that I can comment on their ideas. | 5 | 5 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | [7 empty] | Brian Ee | Keerthigai
As a staff I want to be invisible through my ideas so that I can be free in terms of sharing contents. | 8 | 8 | 0 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | Brian Ee | Kai Lin
As a staff I want to be able to receive confirmation email so that I know I have sucessfully submitted my ideas. | 10 | 10 | 0 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Brian Ee | Kai Lin
Implement "Delete Course" Business Logic (Code) | 0 | 0 | 0
Test for "Delete Course" function | 0 | 0 | 0
Research how to create PDF file | 0 | 0 | 0
Implement create PDF file function (to download) | 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
TOTAL | 31 | 31 | 0 | 1 | 2 | 4 | 4 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 2
Daily burnout | 15.6 |  |  | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1
Total time left (from estimate) |  | Estimate | 31 | 29.9 | 28.8 | 27.7 | 26.6 | 25.5 | 24.4 | 23.3 | 22.2 | 21.1 | 20 | 18.9 | 17.8 | 16.7 | 15.6
Total time left (from spent) |  | Burnout | 31 | 30 | 28 | 24 | 20 | 17 | 14 | 11 | 9 | 7 | 5 | 3 | 2 | 1 | 0

## Sprint 3
Task | Time (estimated) [DAYS] | Time (spent) | Time (left) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | Done By | Tested By
As a staff I want to see the ideas of other people so that I can keep that can react to them. | 8 | 8 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | Kai Lin | Kitty
As a staff I want to be able to choose to be visible so that I can share my ideas to other people. | 8 | 8 | 0 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Kai Lin | Min qi
Implement "Delete Course" Business Logic (Code) | 0 | 0 | 0
Test for "Delete Course" function | 0 | 0 | 0
Research how to create PDF file | 0 | 0 | 0
Implement create PDF file function (to download) | 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
TOTAL | 16 | 16 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2
Daily burnout | 0.6 |  |  | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1
Total time left (from estimate) |  | Estimate | 16 | 14.9 | 13.8 | 12.7 | 11.6 | 10.5 | 9.4 | 8.3 | 7.2 | 6.1 | 5 | 3.9 | 2.8 | 1.7 | 0.6
Total time left (from spent) |  | Burnout | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 8 | 6 | 5 | 4 | 3 | 2 | 1 | 0

## Sprint 4
Task | Time (estimated) | Time (spent) | Time (left) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
As a QA Coordinator I want to be able to access the system so that I am able to track all the latest ideas of staffs. | 2 | 2 | 0 | bar: 2 to 3
As a staff I want to be able choose to be visible so that my ideas can be seen by other people. | 3 | 3 | 0 | 1: 1; 3: 2
As a QA Manager I want to be able to access the system so that I can oversee all the process. | 1 | 1 | 0 | bar: 3
As a QA Manager I want to be able to add new category so that categories will be seen in the main forum page. | 2 | 2 | 0 | bar: 4 to 5
As a QA Manager I want to be able to delete any latest or old ideas so that categories will be reduced once its not being used. | 4 | 4 | 0 | bar: 4 to 7
As a Staff I want to to be able to upload any relevant files to my idea so that uploaded files can be seen in the posted idea. | 3 | 3 | 0 | bar: 6 to 8
As a QA Coordinator I want to be able to upload any relevant files to my idea so that uploaded files can be seen in the posted idea. | 3 | 3 | 0 | bar: 7 to 9
As a QA Coordinator I want to be able to see the statistics of the entire portal so that I can keep track of the overall perfomance of the forum. | 4 | 4 | 0 | bar: 7 to 10
As a QA Manager I want to be able to ban any staffs or coordinators from posting any ideas so that there won't be any inappropriate contents in the forum. | 4 | 4 | 0 | bar: 8 to 11
As a QA Manager I want to be able to upload any relevant files to my idea so that uploaded files can be seen in the posted idea. | 4 | 4 | 0 | bar: 9 to 12
As a QA Manager I want to be able to upload any supporting documents so that I am able to see the files in the idea section. | 2 | 2 | 0 | bar: 12 to 13
As an Admin I want to be able to maintain all the system's data so that system will be up to date. | 1 | 1 | 0 | bar: 14
Implement "List report for CM" Business Logic (Code) | 0 | 0 | 0
Test for "List report - CM" function | 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
TOTAL | 33 | 33 | 0 | 1 | 1 | 4 | 2 | 2 | 2 | 4 | 4 | 4 | 3 | 2 | 2 | 1 | 2
Daily burnout | 12 |  |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
Total time left (from estimate) |  | Estimate | 33 | 31.5 | 30 | 28.5 | 27 | 25.5 | 24 | 22.5 | 21 | 19.5 | 18 | 16.5 | 15 | 13.5 | 12
Total time left (from spent) |  | Burnout | 33 | 32 | 31 | 27 | 25 | 23 | 21 | 17 | 13 | 9 | 6 | 4 | 2 | 1 | 0